## Sheet1
| 2025-09-01 | 2025-10-01 |  |  | 2025-11-01 |  |  | 2025-12-01 |  |  | 2026-01-01 |  |  | 2026-02-01 |  |  | 2026-03-01 |  |  | 2026-04-01 |  |  | 2026-05-01
week | 1 | 10 | 20 | 30 | 10 | 20 | 30 | 10 | 20 | 30 | 10 | 20 | 30 | 10 | 20 | 30 | 10 | 20 | 30 | 10 | 20 | 30 | 10 | 20 | 30
Phase 1: Preparation and Initial Research
Project Proposal
Preliminary Ethics Form
LLM Selection
Dataset Selection
Phase 2: Literature Review and Ethics
LLM Hallucination Definition and Classification
LLM Hallucination Reason
Methods for detecting and alleviating LLM hallucinations
Phase 3: Data Preparation and Baselines
Data Preparation
Baseline Detection Models
Phase 4: Detection Mechanism
Hallucination detection tool selection
Test dataset
Phase 5: Interim Report
Interim Report Writing and Submission
Phase 6: Closed-loop Framework Development
Implement Initial Closed-loop Prototype
Integrate Detection and Mitigation Modules
Run Preliminary Experiments
Analyse Initial Experimental Results
Phase 7: Mitigation Strategy Development
Design Prompt-based Mitigation Strategy
Implement Candidate Generation and Rewriting
Develop Filtering and Reranking Method
Adjust Dataset-specific Mitigation Settings
Phase 8: Evaluation and Benchmarking
Detection Performance Evaluation
Mitigation Performance Evaluation
Ablation Experiments
Cross-dataset Performance Analysis
Phase 9: Dissertation
Dissertation Writing and Submission
Phase 10: Demonstration
Video
Phase 11: Q&A Session
Q&A Session Preparation